## Overview
Backend Solo Roadmap Dashboard
Project timeline and self-management tracker for backend implementation
Metric | Value
Project Start | 2026-04-01
Planned Finish | 2026-08-11
Total Weeks | 19
Owner | Me
Legend | Meaning
Phase Colors | Each phase uses a distinct color band for fast scanning
Status | Track actual execution status
Risk | Use this to highlight blockers early
Priority | Critical items should be protected first
How To Use
Update Status, Progress (%) and Done (Y/N) every Friday.
Only move to the next phase when the exit criteria are truly met.
If a week slips, record the reason in Notes instead of hiding it.
Keep MVP discipline: do not expand scope unless it removes a blocker.

## Weekly Tracker
Week | Start Date | End Date | Phase | Main Objective | Tasks | Deliverable | Dependency | Status | Progress (%) | Risk Level | Priority | Owner | Done (Y/N) | Notes
Week 1 | 2026-04-01 | 2026-04-07 | Phase 0 - Scope & Design | Chot MVP va kien truc ky thuat | Chot danh sach module MVP; chot role Admin/NOC/Captain/Customer; chot DB schema v1; chot MQTT contract v1; chot boundary Next.js/API/Worker | MVP scope v1; schema v1; MQTT contract v1; role matrix v1; API surface v1 | None | Done | 100 | Low | Critical | Me | Y | Completed 2026-03-31; artifacts locked for implementation and stakeholder review
Week 2 | 2026-04-08 | 2026-04-14 | Phase 1 - Infra & Project Setup | Dung nen he thong va khung source | Setup workspace; docker compose local PostgreSQL+MQTT; env template; API/Worker package setup | Project skeleton + local infra baseline | Week 1 | Done | 100 | Medium | Critical | Me | Y | Completed baseline implementation; dependencies installed and runtime verified
Week 3 | 2026-04-15 | 2026-04-21 | Phase 1 - Infra & Project Setup | Hoan thien migration va auth/logging co ban | Tao db migrate/reset scripts; API health+ready; worker ingest raw+heartbeat+telemetry baseline; smoke test script | DB migrate tooling; API readiness; worker ingest baseline | Week 2 | Done | 100 | Medium | Critical | Me | Y | Completed phase1 baseline; ready for Git push and Ubuntu deployment
Week 4 | 2026-04-22 | 2026-04-28 | Phase 2 - MCU Ingest | Dung worker MQTT va ingest heartbeat | Tao worker process rieng; subscribe topic heartbeat; validate payload; save DB; log raw message | Heartbeat ingest hoat dong | Week 3 | Not Started | 0 | High | Critical | Me | N | Lam som bo test payload mau
Week 5 | 2026-04-29 | 2026-05-05 | Phase 2 - MCU Ingest | Mo rong ingest telemetry | Subscribe telemetry; parser; luu metric link status, latency, loss, jitter | Telemetry vao DB dung schema | Week 4 | Not Started | 0 | High | Critical | Me | N | Co the phai sua payload contract voi MCU
Week 6 | 2026-05-06 | 2026-05-12 | Phase 2 - MCU Ingest | Them event ingest va hardening worker | Xu ly event; retry/reconnect; idempotency basic; raw audit | Ingest pipeline on dinh hon | Week 5 | Not Started | 0 | High | Critical | Me | N | Can co bo test duplicate va reconnect
Week 7 | 2026-05-13 | 2026-05-19 | Phase 3 - Package & Usage | Lam package CRUD va quota rule | Tao package CRUD; assign package cho user/nhom; quota model | Package module v1 | Week 6 | Completed | 100 | Medium | Critical | Me | Y | Done 2026-04-16: package CRUD, assign, archive/restore, and /package-catalog split completed.
Week 8 | 2026-05-20 | 2026-05-26 | Phase 3 - Package & Usage | Tinh usage theo user | Build pipeline usage per user; aggregate usage; luu lich su session/usage | User usage v1 | Week 7 | Completed | 100 | High | Critical | Me | Y | Done 2026-04-16: usage aggregation, timeline, export CSV, and filters completed.
Week 9 | 2026-05-27 | 2026-06-02 | Phase 3 - Package & Usage | Quota exhaustion va canh bao co ban | Tinh so du quota; canh bao gan het quota; block rule co ban neu can | Quota tracking v1 | Week 8 | Completed | 100 | High | Critical | Me | Y | Done 2026-04-16: quota tracking, alerts, and assignment lifecycle detail completed.
Week 10 | 2026-06-03 | 2026-06-09 | Phase 3 - Package & Usage | On dinh API va nghiep vu package/usage | Refine API; fix edge cases; test du lieu usage; bo sung audit | Package + usage san sang cho portal | Week 9 | Completed | 100 | Medium | Critical | Me | Y | Done 2026-04-16: audit history and NOC-friendly advanced UX finalized.
Week 11 | 2026-06-10 | 2026-06-16 | Phase 4 - Captain Portal & VMS | Lam captain portal toi thieu | Man hinh login; dashboard crew; user online; quota con lai; usage summary | Captain portal v1 | Week 10 | Not Started | 0 | Medium | High | Me | N | Khong can lam UI dep, chi can ro rang va dung
Week 12 | 2026-06-17 | 2026-06-23 | Phase 4 - Captain Portal & VMS | Them VMS co ban | Luu vi tri, toc do, huong di chuyen, updated_at; view VMS basic | VMS basic tracking | Week 11 | Not Started | 0 | Medium | High | Me | N | Chi can map/list co ban cho pilot
Week 13 | 2026-06-24 | 2026-06-30 | Phase 4 - Captain Portal & VMS | Hoan thien pilot UI cho captain | Sua UI; them filter tau/user; kiem tra scope du lieu theo vessel | Captain portal + VMS basic san sang | Week 12 | Not Started | 0 | Medium | High | Me | N | Dong phase khi captain xem dung du lieu tau minh
Week 14 | 2026-07-01 | 2026-07-07 | Phase 5 - Command Flow & RBAC | Dung command job va ACK | Model command_jobs; publish command MQTT; nhan ACK/result; audit log | Command flow v1 | Week 13 | Not Started | 0 | High | High | Me | N | Nen bat dau tu lenh de test nhu sync package
Week 15 | 2026-07-08 | 2026-07-14 | Phase 5 - Command Flow & RBAC | Hoan thien RBAC | Phan quyen Admin/NOC/Captain/Customer; gioi han tenant/site/vessel scope | RBAC v1 | Week 14 | Not Started | 0 | Medium | High | Me | N | Can test truy cap cheo tenant/site
Week 16 | 2026-07-15 | 2026-07-21 | Phase 5 - Command Flow & RBAC | On dinh luong dieu khien va audit | Refine timeout/retry; bo sung history command; fix bug | Command + RBAC on dinh hon | Week 15 | Not Started | 0 | Medium | High | Me | N | Neu tre co the day mot so lenh nang cao sang backlog
Week 17 | 2026-07-22 | 2026-07-28 | Phase 6 - Staging & Pilot | Kiem thu he thong va staging | Test duplicate/reconnect; test quota exhaustion; test VMS delay; deploy staging | Staging v1 | Week 16 | Not Started | 0 | High | Critical | Me | N | Ghi bug theo muc do anh huong van hanh
Week 18 | 2026-07-29 | 2026-08-04 | Phase 6 - Staging & Pilot | Pilot nho va runbook | Pilot 1-2 site; theo doi log; viet runbook; backup/restore checklist | Pilot run + runbook | Week 17 | Not Started | 0 | High | Critical | Me | N | Khong mo rong neu pilot chua on dinh
Week 19 | 2026-08-05 | 2026-08-11 | Phase 6 - Staging & Pilot | Chot pilot va san sang go-live than trong | Fix bug cuoi; rollback plan; capacity note; go-live checklist | Ready for cautious go-live | Week 18 | Not Started | 0 | Medium | Critical | Me | N | Neu pilot gap loi nghiem trong, gia han phase nay 1-2 tuan

## Phase Summary
Phase | Start Date | End Date | Duration (Weeks) | Goal | Key Deliverables | Exit Criteria | Priority | Notes
Phase 0 - Scope & Design | 2026-04-01 | 2026-04-07 | 1 | Chot pham vi MVP va contract ky thuat | DB schema v1; MQTT contract v1; API surface v1; role matrix v1; MVP scope v1 | Backend, MCU va UI thong nhat payload, topic, schema va scope MVP | Critical | Completed 2026-03-31: full phase0 docs locked for execution
Phase 1 - Infra & Project Setup | 2026-04-08 | 2026-04-21 | 2 | Dung nen Ubuntu, PostgreSQL, MQTT, Next.js | Workspace setup; local compose; db migration/reset scripts; api health/ready; worker ingest baseline; env template; smoke test | He thong dev/staging chay duoc, migrate DB thanh cong, API healthcheck OK | Critical | Completed baseline 2026-03-31: ready to push Git and deploy Ubuntu
Phase 2 - MCU Ingest | 2026-04-22 | 2026-05-12 | 3 | Nhan du lieu heartbeat, telemetry, event tu MCU | Worker subscribe MQTT; validator; ingest pipeline; raw log/audit | MCU test gui du lieu vao DB on dinh, worker reconnect duoc | Critical | Phase de phat sinh sua contract nhieu nhat
Phase 3 - Package & Usage | 2026-05-13 | 2026-06-09 | 4 | Lam nghiep vu package/usage va hoan thien UX cho NOC | Package CRUD; quota logic; user usage; usage aggregation; alert co ban; audit/export; lifecycle detail | Tinh va hien thi duoc usage theo user, quota hoat dong dung, audit/export/lifecycle detail san sang | Critical | Completed 2026-04-16: /dashboard is monitoring-only; /package-catalog handles package operations and advanced reporting.
Phase 4 - Captain Portal & VMS | 2026-06-10 | 2026-06-30 | 3 | Mo giao dien toi thieu cho captain va theo doi VMS | Captain dashboard; user online; quota view; VMS basic tracking | Captain xem duoc du lieu tau minh, VMS hien thi duoc vi tri/trang thai | High | Chi lam dashboard can thiet cho pilot
Phase 5 - Command Flow & RBAC | 2026-07-01 | 2026-07-21 | 3 | Hoan thien luong dieu khien 2 chieu va phan quyen | Command job; ACK/result; RBAC; audit log | Server gui lenh xuong MCU va nhan phan hoi, phan quyen dung | High | Neu tre deadline co the cat bot lenh nang cao
Phase 6 - Staging & Pilot | 2026-07-22 | 2026-08-11 | 3 | Kiem thu, staging, pilot va tai lieu van hanh | Test checklist; staging deploy; pilot rollout; runbook; rollback plan | Pilot on dinh, co the demo/go-live than trong | Critical | Khong go-live rong neu chua qua pilot